## Lessons
Lesson ID | Title | Risk Category | Prior Issue | Cause | Lesson Learned | Source
LL-001 | Front rail weld pitch | Joining / Durability | P1 front rail developed weld fatigue at 60% durability cycles. | Weld pitch selected for static strength, not cyclic load | Set weld pitch from fatigue CAE, not static margin; re-check after any load path change. | Synthetic prior-program record
LL-002 | Formed radius fatigue | Durability | Rear crossmember cracked at 3.5 mm formed radius in P1 durability test. | Radius below formability guideline for HSS at that gauge | Keep formed radii >= 4t for HSS structural members; verify strain with forming simulation. | Synthetic prior-program record
LL-003 | Flange drain path | Corrosion | P1 underbody flanges showed red rust at 40 cycles in corrosion test. | Overlap flange trapped water with no drain | Every horizontal overlap flange needs a drain path or full sealer coverage; review with corrosion team before data release. | Synthetic prior-program record
LL-004 | E-coat venting | Corrosion | P1 rocker inner showed bare metal after e-coat. | Closed section had no vent, coating drained before cure | Apply e-coat standard EC-BIW-002 vent/drain hole pattern to all closed sections. | Synthetic prior-program record
LL-005 | Soft zone location | Crash / Safety | P2 B-pillar intrusion exceeded target in first side crash test. | Hot-stamp soft zone transition placed too low | Lock soft zone location with crash CAE before die release; physical correlation mandatory. | Synthetic prior-program record
LL-006 | UHSS weld schedule | Manufacturing Quality | P2 launch delayed by weld nugget cracks in 1500 MPa PHS. | Standard weld schedule used for UHSS grade | Qualify pulsed weld schedules per WS-JOIN-003 for any grade above 980 MPa before PV build. | Synthetic prior-program record
LL-007 | Strut tower locating | Dimensional | P2 strut tower position drifted during framing, causing alignment complaints. | Locating scheme allowed tower lean | Use net locating hole on strut tower and audit with 30-build capability study. | Synthetic prior-program record
LL-008 | Battery bracket edge distance | Attachment / Durability | P2 battery bracket pulled out in shaker test. | Fastener edge distance only 1.6x hole diameter | Maintain >= 2.5x hole diameter edge distance on battery attachments; add emboss for load spread. | Synthetic prior-program record
LL-009 | Sealer three-layer joint | Corrosion | Water traced into P2 battery compartment at three-layer joint. | Robot sealer path skipped T-joint intersection | Add manual butyl patch at all three-layer T-joints; verify with UV dye water test. | Synthetic prior-program record
LL-010 | Roof gauge weight program | Crash / Safety | P1 roof crush margin eroded by late gauge reduction. | Weight action taken without re-running roof crush CAE | Any gauge change on crash-relevant parts requires CAE gateway re-check before release. | Synthetic prior-program record
LL-011 | Exhaust bracket weld toe | Attachment / Durability | P1 exhaust hanger bracket cracked at weld toe in service fleet. | Weld toe stress riser plus thermal cycling | Use wrap-around welds on hanger brackets; include thermal blocks in durability schedule. | Synthetic prior-program record
LL-012 | Dash crossmember mode | NVH | P2 idle boom traced to dash crossmember first mode at 28 Hz. | Modal target not checked after mass change | Hold first mode >= 32 Hz on steering-support structure; re-check after any added mass. | Synthetic prior-program record